## Slide 1: Team 54: Remote Thermal Viewing within High Voltage Bi-Weekly Update 2 Blake Bagley, Julia Garcia, Erica Mathew Sponsor: Powell Industries TA: Vishwam Raval
Notes: Michelle

## Slide 2: Project description
Problem statement: “As industry demand grows, space inside medium voltage switchgear has become increasingly limited. Manufacturers are required to fit more devices and wires within the same limited space. Additionally, manufacturers are now being asked to include a remote viewing system within the switchgear to monitor a physical ground switch. This ground switch is physically blocked, by wires, from the view of the operator.”
Notes: Erica: Our project sponsor is powell industries which is a “Powell Industries designs and manufactures equipment like switchgear, circuit breakers, and power management systems that help safely control and distribute electrical power in multiple different industries
Switchgears are Switchgears are devices that control and protect electrical circuits by turning power on or off and preventing damage during electrical faults.
Powell industries designs/maufactures
explain switchgears
explain project

## Slide 3: System Overview
Power Supply
Battery
Thermal Sensor
Microcontroller
Website
Julia, Blake, Erica
Converters
Notes: Julia: Design the power supply and overall hardware of the system.
Blake: Microcontroller coding and ML
Erica: Creating Web Application for users to interact with

## Slide 4: Project Timeline
Update #1: Designed and ordered new PCB + started integrating Microcontroller/Website | Update #2: Have PCB soldered and tested + Website/Microcontroller connection | Update #3: Have PCB working and have microcontroller programmed + switch state communication | Update #4: All Integration between subsystems complete | Update #5: Practice Demo + Completing Final Report + Preparing for Showcase
Notes: Eric

## Slide 5: Subsystem 1: PCB Julia
Accomplishments since last update 10 hrs of effort | Ongoing progress/problems and plans until the next presentation
All buck converters soldered All converters tested 3/4 are functional Completed in preparation for integration with microcontroller subsystem | Replace non-functional converter Solder the ESP32 onto the board in preparation for integration with microcontroller subsystem Solder camera socket onto board Test ‘communication’ with ESP32 using oscilloscope

## Slide 6: Subsystem 1: PCB Julia
3 buck converters functional
  Tested using DC power supply
  Voltage in: ~3.7 V
  ESP32
    Expected: 3.3 V
    Measured: 0.04 V
  VDD
    Expected: 2.8 V
    Measured: 2.804 V
  VDDIO
    Expected: 3.1 V
    Measured: 3.061 V
  VDDC
    Expected: 1.2 V
    Measured: 1.205 V
Once the ESP32 and camera socket are soldered onto the board, integration can begin with microcontroller subsystem.

## Slide 7: Subsystem 2: Microcontroller Blake
Accomplishments since last update 17 hrs of effort | Ongoing progress/problems and plans until the next presentation
Found and learned API for communication ("esp_http_client.h") The microcontroller successfully connects to website and can communicate | Next is looking into specific image formatting to send images to the website

## Slide 8: Subsystem 2: Microcontroller Blake
Proof of connection and communication

## Slide 9: Subsystem 3: Website Erica
Accomplishments since last update 15 hrs of effort | Ongoing progress/problems and plans until the next presentation
Achieved connectivity between the microcontroller and website The website successfully received a HTTP POST request from the microcontroller | We are now working on encoding the images creating a system to send/receive the images one by one

## Slide 10: Subsystem 3: Website Erica
Successful Connection:

## Slide 11: Execution plan
 | 1/20/25 | 1/27/25 | 2/3/25 | 2/10/25 | 2/17/25 | 2/24/25 | 3/3/25 | 3/10/25 | 3/17/25 | 3/24/25 | 3/31/25 | 4/7/25 | 4/14/25 | 4/21/25 | 4/28/25
PCB Updated |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Updated PCB ordered |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Parts Ordered |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Researched Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Microcontroller Code Modified |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Website Code Modified |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Status Update #1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
New boards soldered |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Verify Server can receive data from microcontroller |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Buck converters tested |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Website and Microcontroller Connection |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UHMW Polyethylene sheet ordered |  |  |  |  |  |  |  |  | Not Started |  |  |  |  |  | 
Status Update #2 |  |  |  |  |  |  |  |  | In Progress |  |  |  |  |  | 
MCU and Website communication tested |  |  |  |  |  |  |  |  | Completed |  |  |  |  |  | 
PCB and Microcontroller Integration |  |  |  |  |  |  |  |  | Behind |  |  |  |  |  | 
UHMW Polyethylene Box made |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
MCU and Website Communicate Switch State |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Dielectrics Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Status Update #3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Website and Microcontroller Fully Integrated |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Full System Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Status Update #4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Troubleshoot any issues |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Practice Demo |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Status Update #5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Demonstration |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 12: Thank you for listening!